# DiscardLess / MINOUW: accounting for discards in EwE

A limited number of software changes to the Ecopath with Ecosim (EwE) software have been identified to better account for fisheries discarding. The proposed changes are listed in this Google Spreadsheet, and are explained below.

Each task is divided in five sections: 1) priority of the task as established by Discarless and MINOUW members; 2) Description of the task, including questions raised by individual teams in Discardless / MINOUW; 3) assessment of the task and suggestions to possible solutions as discussed in the June 6 expert meeting at the Institute of Marine Sciences (ICM-CSIC), Barcelona, Spain; 4) reevaluation of the June 6 assessment by the EwE programmers, translated into a technical solution; and 5) time estimates to implement the proposed solution.

### Meetings:

- EwE expert meeting, 6 June 2016 - Institute of Marine Sciences (ICM-CSIC), Barcelona, Spain. Participants: Eider Andonegi (DiscardLess, MINOUW, AZTI), Villy Christensen (UBC, EII), Marta Coll (CSIC, EII), Mark Platts (CEFAS, EII), Jeroen Steenbeek (EII)

- EwE teach team meeting, 19 October 2016 (Skype). Participants: Joe Buszowski, Mark Platts, Jeroen Steenbeek

### Document revisions

- 1.0 - Initial June 6 meeting minutes (07 June 2016)

- 1.1 - Included Azores and Balearic feedback (10 October 2016)

- 1.2 - Included EwE tech team meeting notes (20 October 2016)

- 1.3 - Second EwE tech team meeting notes (24 October 2016)

## 1 - Improve discards accounting in Ecopath

Priority:	1 (essential)

Description:	Ecopath internally computes discard proportions using the initial input values of Ecopath for landings and discards, but does not provide this as an output in the Ecopath user interface. This prevents the user from knowing how Ecopath is calculating discards and having this information directly available.

Azores comment: In the discussions we had in Feb 2016, we also mentioned the need to add a column in the discard fate table to allow part of the unwanted catch to be landed, and that possibility should be given to set an economic value to this part of the landings different from the value of the wanted landings. Could it also be included (if it still makes sense)?

June 6 assessment:	The EwE source code will need to be altered to compute and expose the proportion of the catch that is discarded. The current Ecopath > Output > “Quantity” form will be renamed to “Total catch”, and a second form displaying discard proportions (by fleet/gear and group) will be added to Ecopath outputs.

Solution:	It turns out that the Ecopath Quantity form already calculates the discard figures, not Ecopath itself. Ideally, these calculations need to move from the user interface to Ecopath. We need to add an Ecopath fleet output object, data type, etc. We deviate from the june 6 assessment by leaving the Quantity form alone for backwards compatibility reasons. Instead, we’ll add a new form “Total catch” that shows doubly indexed fleet x group ‘Landings, Discard Mortality, Discard Survival, Total Catch’ data. 

As to the Azores comment: it is understood that valuing exported discard fate (representing the value of unwanted catch) is necessary to explicitly model the implications of EU landings obligations. The current EwE setup is able to account for this costing in an indirect way by splitting fleets, etc. Implementation uncertainty is high on this point, mostly because the Ecosim and Ecospace gravity effort logic will be greatly affected, estimated to take 1 to 2 weeks to implement, and a week to test. We cannot address this issue for the provided budget, we will need to find extra funding. Maciej Tomczak (Stockholm University) is interested in writing a follow-up proposal to implement this specific feature.

Estimates:	1.1 Move discard accounting calculations to EwE core
1.2 Expose new calculations in Ecopath group outputs 
1.3 Change Ecopath Output Quantity UI
2 days

## 2 - Add discards accounting to Ecosim

Priority:	1 (essential)

Description:	Ecosim internally accounts for discards and landings using the input values in Ecopath, by fleet/gear, group, and time step. These data are not displayed in the EwE user interface, and are not written to the comma-separated files (CSV files) that Ecosim produces. This prevents the user from knowing how discards and landings have changed over time, and to link them to the observed changes in the ecosystem in order to study the ecosystem impacts of landings and discards.

June 6 assessment:	The EwE source code will need to be altered to expose the landings and discards values as internally computed by Ecosim. Once this change is in place, Ecosim can be made to write these values to CSV file, and the EwE desktop software can display these data in two new graphs in Ecosim > Output > Group plots.

Solution:	A small correction: Ecosim does not explicitly account for discards, but has the bits and pieces to implement this accounting. The Cefas MSE plug-in sorted this out already, for instance. Ecosim output is by group, not by group/fleet. What needs changing: add discard accounting to Ecosim; add “Discard Mortality, Discard Survival” outputs to Ecosim groups, Ecosim output plots; and Ecosim CSV output.

Estimates:	2.1 - Core estimates: 3 days (mostly debugging different F forcing scenarios)
2.2 to 2.5 - UI update group plot + CSV output: 1 day
2.6 - Add Ecosim fleet plots: 2 days (OPTIONAL)

## 3 - Allow varying discards in Ecosim

Priority:	2 (high)

Description:	Once Ecosim discards accounting is in place, users must be able to represent variations in discard strategies, either by varying the proportion discarded, or by changing discard mortality.

June 6 assessment: 	Two new types of forcing functions “discard proportion” and “discard mortality” must be added which both target specific (fleet, group) combinations. Their values will act as multipliers on either the Ecopath discard proportion parameter, or the Ecopath discard mortality rate, during an Ecosim run.

The Ecosim user interface will need to be extended with a discards node in the navigator panel, from where users can review and sketch discards proportions and discards mortality patterns.

The EwE model database format must be changed to store these new forcing functions. Older models that get updated to this new logic must run unaltered, which can be achieved by initializing the new forcing functions with values of 1 (e.g., no relative change to Ecopath parameters) for the duration of the Ecosim run.

Users will want to import values for the discards proportions and discards mortality forcing functions through the regular time series import infrastructure. This will require a few important changes to the format of time series csv files, which must be compatible with earlier CSV file formats.

The shape grids plug-in logic can be augmented to view the newly added, doubly-indexed forcing function types. We consider this to be a low priority addition, pending leftover budget after essential and important changes have been made.

Solution:	Ecosim will copy discard mortalities and discard mortality rates, and would internally use these values instead of the Ecopath versions. We will deviate from the earlier proposed solution, as forcing functions will provide a difficult format to parameterize “discard proportion” and “discard mortality”. Instead, users will control “discard proportion” and “discard mortality” through absolute forcing time series instead. The initial assessment above is correct if “forcing function” is read as “time series”.

Estimates:	3.1 - Changing TS import logic and database to handle second pool code: 2 days
3.2 -  Include double indexing in Ecosim time series logic: 1 day
3.3 - Debugging additions under various F forcing scenarios: 4 days
3.4 - Reflect double indexing in the UI: 2 days
3.5 - Add blocking checks in the two MSE run routines when these new time series are loaded: ½ day

## 4 - Add discards accounting to Ecospace

Priority:	3 (medium) [Azores = priority 2] [Balearic Islands: priority 3]

Description:	Users may want to know when and where discarding is taking place in Ecospace.

June 6 assessment:	Ecospace will need to be changed to explicitly account for discarding. Computed discards will need to be exposed from the Ecospace model, and will need to be displayed in the Run Ecospace user interface. Ecospace will need to be made able to save maps of discard data to file, which should be connected to the Ecospace auto-save system.

Solution:	The “maps of discard data” mentioned in the initial assessment will be “Discard survival” and “Discard mortality”. Ecospace will need to reimplement this, correctly accounting for discard survival etc.

Estimates:	4.1 - Update core computations to account for dying and surviving discards over space aggregated by group: 3 days
4.2 - Update Ecospace run plot to include surviving and dying discards: 1 day
4.3 - Update Ecospace run maps to show surviving and dying discards: 1 day
4.4 - Add discards to autosave structure: ½ day (OPTIONAL)
4.4 - Update Ecological indicators plug-in which will be affected: ½ day (OPTIONAL) 
4.5 - Update Ecospace region export to account for discard survival and discard mortality: ½ day (OPTIONAL)

## 5 - Include landings and discards time series in determining model fit

Priority:	2 (high) [Azores = priority 1] [Balearic Islands = priority 2]

Description:	Rather than driving the Ecosim model with discards (using “discard proportion” or “discard mortality” forcing functions), users may want to use reference time series of absolute total discards and landings for model fitting in addition to the current ability of Ecosim to fit to relative and absolute catches.

June 6 assessment:	This will require addition of two new time series types, Absolute discards and Absolute landings, both by fleet x group.

These time series will be imported through the regular time series import infrastructure. The EwE model database format must be changed to store these new types of time series.

The model fit sum of squares calculations will be extended to include the new time series. The Ecosim > Output > All fits user interface will receive two extra plots, Total Discards and Landings, that visualize the fit of the new types of time series.

Solution:	Assuming that task 3) is in place, this task requires updating the SS computations, adding new panels to the Ecosim all fits plots, and allowing this data to be saved to CSV file.

Estimates:	- Add new time series types and update core SS computations: 2 days
- Updating Ecosim all fits plot + updating CSV file saving: 1 day
- Add reference time series to the Ecosim group plots: 1 day

## 6 - Assess impacts of discards changes to MSE routine

Priority:	4 (low) [Azores = no need?] [Balearic Islands = priority 4]

Description:	The Management Strategy Evaluation (MSE) tool built into EwE implicitly accounts for discarding. It is necessary to assess how the MSE computations and results will be affected by proposed changes in Ecosim and Ecospace. This will need to be explained to the EwE users.

At the June 6 meeting is was presumed that neither DiscardLess nor MINOUW are planning to use the MSE routine, which deemed this a low priority task.

June 6 assessment:	The impact of proposed changes on MSE outputs will need to be assessed, and possible modifications to the MSE routines to explicitly represent discards will need to be identified.

Solution:	Due to low priority this task will not be considered. However, both MSE routines will have to be protected against the new, untested changes as explained in task 3.

Estimates:	- No time required

## 7 - Length-based stanzas to complement age-based stanzas

Priority:	4 (low) [Azores = priority 3] [Balearic Islands = priority 4]

Description:	The current age-based structure of multi-stanza groups as age-groups does not allow for proper accounting of species catchability.

June 6 assessment:	The multi-stanza approach can be extended to provide users with the choice to either use the current age-based life stage structure, or to use a length-based life stage structure. The length-based stanza structure can then be used against a catchability curve.

Solution:	Due to low priority this task will not be considered.

Estimates:	- No time required