## Sheet1
No. | Job | Jb | JS | Critical | Depends | Duration | Description | Notes
1.1 | User Interface |  | 2 | x |  | 2 | Creating tabbed inteface for configuration
1.2 | Code separation | 2 | 0 | x |  | 2 | Separating ERSEM / Netcdf Intererface components with separate GUI
1.3 | Plugin Refactor
1.3.1 | List of Couplerlib interfaces | 1 | 0 | x |  | 1 | Done
1.3.2 | Outline of what and when data needed |  | 1 | x |  | 1 | Reverse of 1.3.1 should match up
1.3.3 | Write Plugin Component |  | 10 | x | 1.32 & 1.31 & 1.2 & 1.1 | 10
1.3.4 | Test with Couplerlib and Tweek | 2 | 2 | x | 1.3.3 | 2
1.4 | Paths & User config |  | 2 | x | 1.2 | 2 | for usability
1.5 | NetCDF | 5 | 2 | x | 1.3&1.4 |  | For OPEC
2.1 | Online Mode | 40 |  |  | 1.3 & 1.4 |  |  | Also depends on COSMIC ME project
19